## 14.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 14.11.2022
Alessia | examined the repository in order to understand the task | define the tasks together | the repository is rather confusing, | Present | all
Berk | examined the repository. He found the data source within the repository and shared it | define the tasks together |  | Late | none
Hannah | examined the repository in order to understand the task | define the tasks together |  | Absent | none
Julia | Emailed the teacher about Epic 2, received an answer and shared it. Examined the repository. | define the tasks together
Thorsten | examined the repository in order to understand the task | define the tasks together | the repository is rather confusing
New meetings
Participants | Topic | Time
Everybody | Daily Scrum meeting

## 15.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 15.11.2022
Alessia | This meeting was replaced with a meeting to define the tasks together! |  |  | Present | all
Berk |  |  |  | Late | none
Hannah |  |  |  | Absent | none
Julia
Thorsten
New meetings
Participants | Topic | Time
Everybody | Daily Scrum meeting | 16.11.2022, 18:10

## 16.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 16.11.2022 | 18:15
Alessia | None | Merge data | None | Present | all
Berk | Visualised a proposed workflow, looked at Code |  | No merged data available to look at. Wants to discuss again the worklfow and the tasks. | Late | none
Hannah |  |  |  | Absent | none
Julia | Obtained the data and uploaded it in a new repository. |  | Should I create a new repository?
Thorsten | None | Look at NaNs | NLA: No time left for anything else.
New meetings
Participants | Topic | Time
Everybody | Daily Scrum meeting

## 17.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 17.11.2022 | 14:00
Alessia | Nothing | Look at the categories today. |  | Present | all
Berk | Created code to download the data and merge it. Tried to upload it. Created a new branch. Edited Issue 1. | Discuss about the pipeline sketch with the team. | The file was too big to upload it to github. | Late | none
Hannah | Started with checking the correlations | Continue checking the correlations | The code still contains errors. | Absent | none
Julia | Nothing | Look at the distribution | Do we want to store the data seperatly or not?
Thorsten | Tried to find the merged data to check the NANs. | Try again checking the NaNs | The merged data was not available
New meetings
Participants | Topic | Time | Comments
Everybody | Daily Scrum meeting | 18.11.2022, 13:45
Everybody | Discuss the pipeline | 17.11.2022, 14:30 | We could clarify the task further and developed a model for a reccomender based on nn.

## 18.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 18.11.2022 | 14:00
Alessia | checked the genres | Dealing with missing values | there are several genres, how do we treat them? We need to convert the time. We need to change data types of certain categories, e.g. integer for id etc. | Present | Berk, Alessia,Thorsten
Berk | No time. Did the NANs | Summarize the data visually | No time to look at the data. | Late | Hannah(14:10)
Hannah | Tried to look at the distributions, merging the data first. | Retry | Did not found the merged data to download. Wants to discuss github again | Absent | Julia (excused)
Julia
Thorsten | Philosophed about the data and how to use the NANs. Are the NaNs actually a problem? Depends on the reccomender. Tags have many NaNs. | Look at outliers.
New meetings
Participants | Topic | Time | Remarks
Everybody | Daily Scrum meeting | 21.11.2022 13:45
Everybody | Estimate Tasks | 14:30 | We estimated the time of the rest of the tasks. It took longer than expected.
Everybody + Teacher | Receive feedback and clarify questions | 15:00 | We should use the spotlight code snippets for the models and focus more on the Agile methodologies. We discussed what a reccomender is. For now, we treat it as a classifier, where the five different ratings are the classes. One Issue is one task. There should be one feature per branch. Continuous Integration: Update the branches regularly. Update the SCRUMBAN individually. Update the Sprint Backlog together. There are two reccomender types: Which movies are similar or which users have similar behaviour?

## 21.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 21.11.2022 | 13:45
Alessia |  |  |  | Present | Thorsten, Berk
Berk | Tried to run the spotlight reccomender, tested differet models. Read into the documentation of spotlight. Worked on a visualization for the data in Jupyter Notebook. Tried to implement it into a pipeline to make it usable on new data. | Continue working on the visualization pipeline. Changes the settings for the repository. |  | Late | None
Hannah |  |  |  | Absent | Hannah (excused), Alessia, Julia
Julia
Thorsten | Fixed issues with his environment. Created a new one, ran the reccomender code. Updated the Daily Meeting records. Tried to look at the outliers. Tried to understand the code of Berk and its purpose. Tried to upload the Agile Methods documentation. | Upload the daily meeting record. Discuss the preparation of the Demo with the team! | Did not find any code snippets that would allow looking at the outliers. Knows that they exist, because Berk showed them the last time. Did not understand the commits of Berk and how they can be used. DOES NOT HAVE PUSH ACCESS!
New meetings
Participants | Topic | Time | Remarks
Everybody | Daily Scrum meeting | 22.11.2022, 13:00
Everybody | Discuss Demo preparation | 22.11.2022 after Daily Scrum
Berk, Thorsten | Access to Berk's code. | 22.11.2022 TBA

## 22.11.2022
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date: | 22.11.2022 | 13:00
Alessia | Tried to run the spotlight code. | Discuss the output with the team. | Did not understand the numbers of the outcome. | Present | Alessia, Berk, Julia, Thorsten
Berk | Tried to run the spotlight code. They are using preprocessed data, and there are many columns omitted. The output is the index of the movie. Tried to implement code for the visualization with branch one. Uploaded the code. The code takes the data and returns some plots. Saves the result in a pdf. | Discuss about the demo with the team, re-prioritize demo-related tasks and pick one. | The trained model does not give a specific movie_id as a reccomender. | Late | None
Hannah |  |  |  | Absent | Hannah (connection)
Julia | None | Look at the distribution. | Was sick, could not do the task.
Thorsten | Retried to push. | Fix the push issue.
New meetings
Participants | Topic | Time | Remarks
Everybody | Daily Scrum meeting | 22.11.2022, 13:00
Everybody | Discuss Demo preparation | 22.11.2022 after Daily Scrum, 18:10
Berk, Thorsten | Access to Berk's code. | 22.11.2022 18:10

## Template
Daily SCRUM meeting of the Agile Data Science Project - group 4 |  |  |  | Sprint | 1
Names | What did you do? | What do you plan to do next? | Which problems occured? | Date:
Alessia |  |  |  | Present
Berk |  |  |  | Late
Hannah |  |  |  | Absent
Julia
Thorsten
New meetings
Participants | Topic | Time | Remarks
Everybody | Daily Scrum meeting